STATEMENT OF WORK OUTLINE TEMPLATE

| PROJECT TITLE | 3D Virtual Tour Sharing Platform |  |  |
| --- | --- | --- | --- |
| COMPANY NAME | University Project | CLIENT | University Project |
| PROJECT MANAGER | Ahmed Raza | DATE SUBMITTED | 15-05-2026 |
| AUTHOR | Rabia Khalid | VERSION | 1.0.0 |
| PROJECT BEGIN DATE | 22-11-2025 | END DATE | 23-05-2026 |

- INTRODUCTION

The purpose of this project is to design and develop a mobile application that enables users to create, manage, and share immersive 360-degree panoramic content. The system aims to provide an interactive and user-friendly environment where individuals and businesses can showcase locations, products, or experiences virtually.

This project focuses on enhancing digital visualization by allowing users to explore environments remotely through their mobile devices, improving accessibility, engagement, and decision-making. The application will support content creation, customization, and secure sharing while ensuring performance, usability, and scalability.

  - Project Overview

The necessity of this project arises from the increasing demand for virtual experiences in industries such as real estate, tourism, education, and e-commerce. Traditional media such as images and videos often fail to provide a fully immersive understanding of spaces, especially for users who rely on mobile access.

With the widespread use of smartphones and the growing importance of mobile applications, there is a strong need for a platform that allows users to interact with environments in a more engaging and realistic way directly from their devices. This project addresses these challenges by providing a centralized mobile application where users can upload panoramic content, organize it efficiently, and share it with others.

  - Scope of Work

The project involves the complete development of a mobile application that supports panoramic content creation, management, and sharing. It includes system design, development, testing, and deployment phases.

    - Inclusions (What is included in the project)

- User Account Management

The application will provide functionality for users to register, log in, and manage their profiles. It will include secure authentication mechanisms and allow users to update personal details and manage account settings within the mobile app.

- Panorama Upload and Management

Users will be able to upload 360-degree panoramic images directly from their mobile devices and organize them into a structured content library. The system will allow users to edit, rename, and categorize panoramas for better organization.

- Interactive Viewing Experience

The mobile application will include an interactive viewer that allows users to explore panoramic content smoothly using touch gestures such as swipe, zoom, and rotation, creating an immersive experience.

- Privacy and Access Control

Users will be able to control the visibility of their content by setting it as public, private, or restricted. This ensures proper privacy management within the application.

- Search and Discovery Features

The system will provide search functionality and categorization options to help users easily find and explore panoramic content within the app.

- System Testing and Deployment

The project includes testing phases to ensure app performance, usability, and reliability across mobile devices. After testing, the application will be deployed for user access.

    - Exclusions (What is not included in the project)

- Web Application Development

This project does not include the development of a web-based version of the system. The focus is solely on the mobile application.

- Advanced AI-based Image Processing

The application will not include advanced AI features such as automatic panorama stitching, object recognition, or smart editing.

- Third-party Hardware Integration

Integration with external devices such as VR headsets or professional 360-degree cameras is not included in this phase.

- Payment or Subscription Systems

The app will not include payment gateways, subscriptions, or monetization features.

- Large-scale Cloud Infrastructure

The project will not cover enterprise-level cloud scaling or distributed infrastructure beyond basic backend support.

1.3 Objectives

| OBJECTIVE | RATIONALE |
| --- | --- |
| Develop a user-friendly mobile application for managing panoramic content | To ensure that users can easily create, upload, and organize their content without requiring technical expertise |
| Provide an immersive and interactive viewing experience | To enhance user engagement by allowing realistic exploration of 360-degree environments through mobile devices |
| Ensure secure user authentication and data privacy | To protect user data and maintain trust by implementing secure login and access control mechanisms |
| Enable efficient organization and sharing of panoramic content | To allow users to manage their content effectively and share it with others in a convenient manner |
| Design an intuitive interface for all types of users | To make the application accessible and easy to use for both technical and non-technical users |
| Deliver a reliable and high-performance mobile application | To ensure smooth functionality, minimal errors, and a positive user experience |
| Build a scalable system for future enhancements | To allow future integration of advanced features such as AI tools, VR support, or additional functionalities |

1.4 Deliverables(Final Outputs)

| # | DELIVERABLE | DESCRIPTION |
| --- | --- | --- |
| 1 | Mobile Application (Final Product) | Fully functional mobile app for 360° panoramic content creation, management, and sharing |
| 2 | User Authentication Module | Secure registration, login (email/phone/social), password reset, 2FA, logout from all devices |
| 3 | Panorama Upload Module | Upload 360° panoramic images and videos from device with compression options |
| 4 | Panorama Management Module | Organize, edit, rename, categorize, delete, and apply filters to panoramic content |
| 5 | Interactive Viewer Module | 360° viewer with touch gestures: zoom, swipe, rotate, and full-screen mode |
| 6 | Virtual Tours & Storytelling Module | Create virtual tours by linking multiple panoramas; sequential scene navigation; add descriptions |
| 7 | Interactive Hotspots Module | Add clickable hotspots inside panoramas with text, audio, or video popups |
| 8 | Social Interaction Module | Like, comment, share, follow/unfollow, real-time messaging, group chats, block users |
| 9 | Privacy and Access Control Module | Public/private/restricted visibility, content access permissions, account privacy settings |
| 10 | Search and Discovery Module | Search by keywords/categories/hashtags; browse trending content; AI-based recommendations |
| 11 | Profile Insights Module | View likes, comments, views, follower growth, and content popularity analytics |
| 12 | Notification Module | Push notifications for likes, comments, follows, messages, and platform announcements |
| 13 | Admin & Moderation Panel | Review reported content, manage user accounts, issue warnings/blocks, broadcast announcements |
| 14 | User Interface (UI/UX Design) | Intuitive design, smooth navigation, onboarding tour, accessible layouts |
| 15 | Testing and Quality Assurance Reports | Unit testing, integration testing, UAT results, bug reports, performance metrics |
| 16 | Deployment Package | Final APK (Android) / IPA (iOS) ready for installation and store submission |
| 17 | Documentation | Complete SRS, user guide, technical documentation, API documentation |

- PROJECT SCHEDULE

  - Phase 1: Planning, Design & Core System Setup

| TASK ID | TASK DETAIL | START DATE | END DATE | DELIVERABLE DESCRIPTION |
| --- | --- | --- | --- | --- |
| 2.1 | Requirement Analysis & Feature Finalization | 1 Apr 2026 | 4 Apr 2026 | Complete list of system modules and features (User, Panorama, Social, etc.) |
| 2.2 | System Architecture & Database Design | 5 Apr 2026 | 9 Apr 2026 | Backend structure, database schema, and system workflow |
| 2.3 | UI/UX Design (Mobile App Screens) | 10 Apr 2026 | 15 Apr 2026 | UI designs for login, profile, feed, viewer, chat, and settings screens |
| 2.4 | Development Environment Setup | 16 Apr 2026 | 17 Apr 2026 | Tools, frameworks, and development environment configured |

  - Phase 2: Core Modules Development

| TASK ID | TASK DETAIL | START DATE | END DATE | DELIVERABLE DESCRIPTION |
| --- | --- | --- | --- | --- |
| 2.5 | User Management Module Development | 18 Apr 2026 | 22 Apr 2026 | User registration, login, profile, follow system |
| 2.6 | Panoramic Content Management Module | 23 Apr 2026 | 28 Apr 2026 | Upload, edit, delete, organize panoramas |
| 2.7 | Panorama Viewing Module | 29 Apr 2026 | 2 May 2026 | Interactive 360° viewer |
| 2.8 | Virtual Tours & Storytelling Module | 3 May 2026 | 6 May 2026 | Virtual tours and scene linking |
| 2.9 | Interactive Features Module | 7 May 2026 | 9 May 2026 | Hotspots and clickable elements |
| 2.10 | Social Interaction Module | 10 May 2026 | 14 May 2026 | Likes, comments, chat system |

  - Phase 3: Advanced Features, Testing & Deployment

| TASK ID | TASK DETAIL | START DATE | END DATE | DELIVERABLE DESCRIPTION |
| --- | --- | --- | --- | --- |
| 2.11 | Profile Insights Module | 15 May 2026 | 16 May 2026 | Analytics for views, likes, engagement |
| 2.12 | Search & Discovery Module | 17 May 2026 | 19 May 2026 | Search, trending, categories |
| 2.13 | Notification Module | 20 May 2026 | 21 May 2026 | Alerts for activity and updates |
| 2.14 | Settings & Privacy Module | 22 May 2026 | 23 May 2026 | Privacy controls and account settings |
| 2.15 | Admin & Moderation Module | 24 May 2026 | 26 May 2026 | Admin controls and moderation system |
| 2.16 | Integration of All Modules | 27 May 2026 | 29 May 2026 | Fully integrated application |
| 2.17 | Testing & Quality Assurance | 30 May 2026 | 3 Jun 2026 | Bug fixing and optimization |
| 2.18 | Final Deployment | 4 Jun 2026 | 5 Jun 2026 | Final mobile app release |
| 2.19 | Documentation & Submission | 6 Jun 2026 | 7 Jun 2026 | Complete documentation |

- KEY CHECKPOINTS

- Requirements and system features finalized and approved

- System architecture and database design completed

- UI/UX design approved

- User authentication system successfully implemented

- Panorama upload and management features functional

- Interactive panorama viewer working smoothly

- Virtual tours and storytelling features completed

- Social interaction features (likes, comments, chat) operational

- Search and discovery features implemented

- Privacy and settings features functioning correctly

- Admin and moderation system ready

- All modules successfully integrated into one system

- Application tested, optimized, and bug-free

- Final mobile application deployed successfully

- Project documentation completed and submitted

- ROLES & RESPONSIBILITIES

| NAME - ROLE | RESPONSIBILITIES | COMMENTS |
| --- | --- | --- |
| Rabia Khalid – Project Manager | Oversee project execution, manage schedule, coordinate between teams, approve milestones | Responsible for overall project delivery |
| Ali Khan – UI/UX Designer | Design mobile app screens, wireframes, user flows, and interface prototypes | Works closely with developers to ensure usability |
| Sara Ahmed – Frontend / Mobile Developer | Implement user interface, interactive modules, and mobile functionalities | Focused on Android/iOS development and app responsiveness |
| Usman Iqbal – Backend / API Developer | Develop server-side logic, database integration, APIs for authentication, content management, notifications | Ensure data security and smooth module integration |
| Hina Riaz – QA / Testing Team Lead | Test all modules, report bugs, verify fixes, perform performance and usability testing | Ensures bug-free and optimized application |
| Client / End Users – 3DPanoSphere Beta Testers | Provide requirements, review milestones, give feedback on features and usability | Approves designs and validates functionality |
| Dr. Jane Matthews – Stakeholder / Supervisor | Monitor project progress, approve deliverables, provide strategic guidance | Includes university/project advisor |
| Bilal Shah – Content / Multimedia Team | Prepare 360° images, videos, virtual tours, interactive hotspots | Ensures high-quality content for the app |
| Fatima Noor – Admin / Moderation Team | Manage platform activities, review reported content, ensure system security and compliance | Monitors app safety and user compliance |
| Ayesha Tariq – Documentation Team | Prepare project reports, user guides, technical documentation | Ensures proper knowledge transfer and submission readiness |

- TERMS OF PAYMENT

- Fee Summary

The total fee for the development and delivery of the 3DPanoSphere mobile application is $2,680 (PKR 742,000). This fee encompasses all aspects of the project including planning, system design, mobile application development, testing, deployment, and documentation. It covers personnel costs for the project team, including the Project Manager, UI/UX Designer, Frontend and Backend Developers, QA team, Content Team, and Documentation team. Additionally, the fee includes costs associated with cloud storage for 360° panoramic content, server setup, implementation, and training of client personnel or end-users.

All costs are aligned with the project scope and timeline, and the fee is structured to be milestone-based to ensure transparency, accountability, and timely delivery of project outputs.

- Storage, Personnel, Training, Implementation Costs

The total project fee of $2,680 (PKR 742,000) includes all necessary costs to successfully deliver the 3DPanoSphere mobile application.

- Storage Costs:

This covers cloud storage required to host 360° panoramic images and videos, ensuring secure and reliable access for all users.

- Personnel Costs:

Includes salaries and compensation for the project team, comprising the Project Manager, UI/UX Designer, Frontend and Backend Developers, QA team, Content team, and Documentation team.

- Training Costs:

Covers training sessions for client personnel and end-users to familiarize them with the mobile application features, navigation, and content management.

- Implementation Costs:

Encompasses system setup, server configuration, application deployment, and integration of all modules, ensuring the app functions seamlessly upon release.

- Fee Breakdown

| RATE SCHEDULE |  |  |
| --- | --- | --- |
| ESTIMATED COST | DELIVERY SCHEDULE | DESCRIPTION |
| $380 / 105,000 PKR | 01–4 Apr 2026 | Requirement analysis and feature finalization |
| $420 / 116,000 PKR | 05–15 Apr 2026 | System architecture, database design, and UI/UX design |
| $800 / 222,000 PKR | 16 Apr – 14 May 2026 | Core module development (User Management, Panorama Content, Viewing, Virtual Tours) |
| $600 / 166,000 PKR | 15–26 May 2026 | Advanced modules (Interactive Features, Social Interaction, Profile Insights, Search, Notification, Settings, Admin) |
| $420 / 116,000 PKR | 27 May – 5 Jun 2026 | Integration, Testing, Quality Assurance, and Final Deployment |
| $60 / 17,000 PKR | 06–7 Jun 2026 | Documentation and submission |
| PAYMENT TERMS |  |  |
| COMPLETION DATE | PAYMENT DUE | PHASE / WORK DESCRIPTION |
| 04 Apr 2026 | $380 / 105,000 PKR | Completion of requirement analysis and feature finalization |
| 15 Apr 2026 | $420 / 116,000 PKR | System architecture, database design, and UI/UX approval |
| 14 May 2026 | $800 / 222,000 PKR | Completion of core module development |
| 26 May 2026 | $600 / 166,000 PKR | Completion of advanced modules |
| 05 Jun 2026 | $420 / 116,000 PKR | Completion of integration, testing, and deployment |
| 07 Jun 2026 | $60 / 17,000 PKR | Submission of documentation and project closure |

- PROJECT REQUIREMENTS

6.1 Agency Responsibilities

- Planning, designing, developing, testing, and deploying the 3DPanoSphere mobile application.

- Ensuring all modules are implemented according to approved features and specifications.

- Providing UI/UX designs, technical documentation, and training materials.

- Managing cloud storage, system integration, and server setup for panoramic content.

- Conducting quality assurance, bug fixing, and optimization of the mobile app.

- Providing milestone-based progress reports and updates to the client.

6.2 Client Responsibilities

- Providing clear project requirements, feedback, and approvals at each milestone.

- Supplying 360° panoramic content, videos, and any additional multimedia assets.

- Coordinating with end-users for beta testing and feedback.

- Ensuring timely payment according to the agreed Terms of Payment.

- Reviewing deliverables and reporting any issues or required changes.

6.3 Mutual Responsibilities

- Both the agency and the client will jointly ensure:

- Effective communication and regular status updates throughout the project lifecycle.

- Adherence to project schedule, deadlines, and milestone approvals.

- Prompt resolution of any issues, queries, or technical obstacles.

- Maintaining confidentiality and data security standards for all content and user data.

- Collaborative approach in testing, deployment, and training sessions to ensure successful project completion.

- PROJECT RISKS

| PROJECT RISKS |  |
| --- | --- |
| ISSUE / RISK | MITIGATION / CONTINGENCY |
| Delay in content delivery | Set clear deadlines for client-provided content |
| Technical issues during module integration | Conduct integration in phases |
| Mobile app crashes or bugs | Implement thorough QA and testing for each module |
| Security vulnerabilities | Use secure APIs, encrypted storage, and authentication |
| Team unavailability | Maintain backup resources; cross-train team members to handle multiple roles |
| Changes in project requirements | Document all requirements upfront |
| Slow app performance with large panoramic content | Optimize media files |
| Client delays in milestone approvals | Set milestone review timelines in advance |
| Compatibility issues across devices | Conduct device compatibility testing |
| Unexpected additional costs | Maintain contingency budget |

- ACCEPTANCE CRITERIA

- All modules (User Management, Panoramic Content, Viewing, Virtual Tours, Social Interaction, Admin) must be fully implemented and functional according to SOW specifications.

- The mobile app must pass all QA tests, including functional, usability, performance, and security testing.

- The client must review and approve milestone deliverables within the agreed timeframe.

- The application must be fully deployable on Android/iOS with no critical bugs.

- Documentation, training materials, and user manuals must be complete and approved by the client.

- All contractual obligations, privacy adherence, and regulatory requirements must be met before final acceptance.

- STANDARDS AND COMPLIANCE

- Communications Plan

- Regular project updates will be communicated to the client and stakeholders via email, scheduled meetings, and progress reports.

- Milestone reviews will be conducted at the end of each phase.

- Slack or Microsoft Teams (or agreed platform) will be used for real-time communication among team members.

- Quality Management Plan

- All modules of the 3DPanoSphere mobile app will undergo thorough testing: unit testing, integration testing, and user acceptance testing.

- Bug tracking and resolution will be maintained throughout the project lifecycle.

- Quality standards are aligned with mobile app development best practices.

9.3 Training Plan

- End-users and client personnel will receive training sessions on app functionality, uploading panoramas, managing virtual tours, and using interactive features.

- Training will include user manuals, video guides, and live demonstrations.

  - Standard Compliance

- The mobile app will follow industry coding and design standards, including modular programming, clean architecture, and responsive UI.

- Naming conventions, documentation, and version control will follow professional software engineering practices.

- BUSINESS TERMS / CONDITIONS

9.5 Contract Modifications

- Any changes to project scope, deliverables, or timeline must be documented and approved by both the agency and client.

- Formal change requests will define the impact on cost and schedule.

9.6 Confidentiality

- All project-related information, source code, and client data are confidential.

- Team members and stakeholders are bound by a non-disclosure agreement (NDA).

9.7 Termination

- Either party may terminate the project if agreed milestones are not met, or breach of contract occurs.

- Termination conditions, notice period, and obligations will follow the agreed contract terms.

- AUTHORIZATION

| AUTHORIZATION |  |  |
| --- | --- | --- |
| CLIENT | SIGNATURE |  |
|  | PRINTED NAME |  |
|  | DATE |  |
| PROVIDER | SIGNATURE |  |
|  | PRINTED NAME |  |
|  | DATE |  |

DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.